## Risk Register
Green Security Group · Business Security Risk Register
greensecuritygroup.com · paul@greensecuritygroup.com · Paul Green, CISSP
ID | Date | Area | What is the risk? | Where does it come from? | How likely? (1-5) | How bad? (1-5) | Score (F x G) | Level | Owner | What is the plan to fix it? | Target Date | Status
R-001 |  | Protecting Your Physical Space | No lock on the room where servers and network equipment are kept | Anyone who enters the office | 3 | 4 |  |  | Owner | Install a keyed lock on the server room. Limit who has a key. |  | Open
R-002 |  | Protecting Your Physical Space | No record kept of who accesses the server room and when | Internal | 2 | 3 |  |  | Office Manager | Start a simple paper visitor log. Review it monthly. |  | Open
R-003 |  | Controlling Who Can Access What | Multiple staff share the same login for key systems | Internal | 4 | 5 |  |  | Owner | Create individual logins for every staff member. Remove shared accounts. |  | Open
R-004 |  | Controlling Who Can Access What | Two-step verification not turned on for business email | External | 4 | 5 |  |  | Owner | Enable two-step verification in Microsoft 365 or Google Workspace today. |  | Open
R-005 |  | Controlling Who Can Access What | Former employee accounts not removed when they left | Internal | 3 | 4 |  |  | Owner / HR | Disable accounts on the last day of employment. Add to offboarding checklist. |  | Open
R-006 |  | Controlling Who Can Access What | No written password rules — staff use whatever they want | Internal | 3 | 4 |  |  | Owner | Distribute and enforce the Password Policy. Set up a business password manager. |  | Open
R-007 |  | Securing Your Network and Devices | Using a basic home-style router, not a business firewall | External | 4 | 5 |  |  | IT Provider | Replace with a business-grade firewall. Ask your IT provider for a recommendation. |  | Open
R-008 |  | Securing Your Network and Devices | Customer Wi-Fi is on the same network as business systems | External | 3 | 4 |  |  | IT Provider | Set up a separate guest Wi-Fi network. Keep customers off the business network. |  | Open
R-009 |  | Securing Your Network and Devices | Remote access to business systems is not secured properly | External | 5 | 5 |  |  | IT Provider | Implement a business VPN. Remove any direct remote access that is not protected. |  | Open
R-010 |  | Securing Your Network and Devices | Security software on business computers is outdated | External | 3 | 4 |  |  | IT Provider | Update security software on all devices. Enable automatic updates. |  | Open
R-011 |  | Protecting Your Business Information | Business data is only backed up locally — no offsite copy | External | 4 | 5 |  |  | Owner | Set up cloud backup (Backblaze B2 is a good option). Test restoration quarterly. |  | Open
R-012 |  | Protecting Your Business Information | Laptops are not encrypted — stolen device = exposed data | External | 3 | 5 |  |  | IT Provider | Enable BitLocker (Windows) or FileVault (Mac) on all laptops. |  | Open
R-013 |  | Protecting Your Business Information | No policy for how long to keep records or how to dispose of them | Internal | 2 | 3 |  |  | Owner | Write a simple data retention policy. Implement secure shredding for documents. |  | Open
R-014 |  | Being Ready When Something Goes Wrong | No written plan for what to do if there is a cyberattack | External | 4 | 4 |  |  | Owner | Customize and distribute the Incident Response Plan (GSG-03). Walk through it as a team. |  | Open
R-015 |  | Being Ready When Something Goes Wrong | No cyber insurance coverage | External | 3 | 5 |  |  | Owner | Get quotes from at least two cyber insurance providers. |  | Open
R-016 |  | Managing Your Outside Vendors | No list of which vendors or software tools can access business data | External | 3 | 4 |  |  | Owner | Make a simple vendor inventory. Review access quarterly. |  | Open
R-017 |  | Managing Your Outside Vendors | Vendor contracts do not require them to protect our data | External | 2 | 4 |  |  | Owner | Add data protection clauses to vendor contracts at next renewal. |  | Open
R-018 |  | Building a Security-Aware Team | Staff have never received security awareness training | Internal | 4 | 4 |  |  | Owner | Run an annual awareness session. Enroll in KnowBe4 or CISA free resources. |  | Open
R-019 |  | Building a Security-Aware Team | No practice phishing tests to see how staff respond | Internal | 3 | 4 |  |  | Owner | Run a practice phishing test. Use results to target additional training. |  | Open
R-020 |  | Staying Safe in Cloud and Remote Work | Two-step verification not turned on for cloud platforms | External | 5 | 5 |  |  | Owner | Enable two-step verification for all cloud accounts — especially admin accounts. |  | Open

## How to Use
Green Security Group · Risk Register — How to Use
greensecuritygroup.com · paul@greensecuritygroup.com
HOW LIKELY IS THIS? (Column F)
Score | Likelihood | Description
1 | Very Unlikely | Has not happened before and is unlikely in the next year
2 | Unlikely | Could happen but probably will not this year
3 | Possible | Could realistically happen within the next 12 months
4 | Likely | Likely to happen at least once in the next year
5 | Almost Certain | Has happened recently or is expected imminently
HOW BAD WOULD IT BE? (Column G)
Score | Impact | Description
1 | Minimal | Minor disruption — resolved quickly with no lasting effect
2 | Minor | Some disruption but manageable without major cost or effort
3 | Moderate | Significant disruption — requires real effort and cost to fix
4 | Serious | Major harm to operations, finances, or client relationships
5 | Severe | Could threaten the survival or reputation of the business
WHAT YOUR SCORE MEANS (Column H = F x G)
Score | Level | What to Do
20-25 | CRITICAL | Act immediately. This is a serious gap that needs urgent attention.
12-19 | HIGH | Address within 30 days. Assign a named owner and track it actively.
6-11 | MEDIUM | Plan to address within 60-90 days. Include in your next review cycle.
1-5 | LOW | Monitor and review quarterly. Accept with a written note if cost to fix exceeds the risk.