## Risk Register
GREEN SECURITY GROUP · RISK REGISTER
greensecuritygroup.com · paul@greensecuritygroup.com · Paul Green, CISSP
Risk ID | Date Added | Domain | Risk Description | Threat Source | Likelihood (1-5) | Impact (1-5) | Risk Score (F×G) | Risk Level | Assigned Owner | Mitigation Action | Target Date | Status
R-001 |  | Physical Security | No lock on server room door | Internal / External | 3 | 4 |  |  | IT Manager | Install keyed lock on server room. Restrict key access to authorized personnel only. |  | Open
R-002 |  | Physical Security | No visitor log for server room access | Internal | 2 | 3 |  |  | Office Manager | Implement a paper visitor log. Review monthly. |  | Open
R-003 |  | Access Controls | Shared admin account used by multiple staff | Internal | 4 | 5 |  |  | IT Manager | Create individual admin accounts. Disable shared account. |  | Open
R-004 |  | Access Controls | MFA not enabled on email platform | External | 4 | 5 |  |  | IT Manager | Enable MFA via Microsoft 365 Security Defaults or Google Workspace Admin Console. |  | Open
R-005 |  | Access Controls | Former employee accounts not disabled promptly | Internal | 3 | 4 |  |  | HR / Manager | Add account disabling to offboarding checklist. Audit quarterly. |  | Open
R-006 |  | Access Controls | No password policy documented or enforced | Internal | 3 | 4 |  |  | IT Manager | Distribute and enforce GSG Password Policy. Deploy password manager. |  | Open
R-007 |  | Network Defenses | Consumer-grade router in use — no firewall | External | 4 | 5 |  |  | IT Manager | Replace with business-grade firewall. Document firewall rules. |  | Open
R-008 |  | Network Defenses | Guest and business Wi-Fi on same network | External | 3 | 4 |  |  | IT Manager | Configure separate guest SSID/VLAN. Block guest access to internal resources. |  | Open
R-009 |  | Network Defenses | RDP (port 3389) exposed to the internet | External | 5 | 5 |  |  | IT Manager | Disable public RDP exposure immediately. Implement VPN for remote access. |  | Open
R-010 |  | Network Defenses | Endpoints running outdated antivirus | External | 3 | 4 |  |  | IT Manager | Deploy Microsoft Defender for Business or equivalent EDR on all endpoints. |  | Open
R-011 |  | Data Protection | No offsite backup — local backup only | External | 4 | 5 |  |  | IT Manager | Implement cloud backup (e.g. Backblaze B2). Test restoration quarterly. |  | Open
R-012 |  | Data Protection | Sensitive data not encrypted on laptops | External | 3 | 5 |  |  | IT Manager | Enable BitLocker (Windows) or FileVault (Mac) on all laptops. |  | Open
R-013 |  | Data Protection | No data retention or disposal policy | Internal | 2 | 3 |  |  | Manager | Draft and distribute data retention policy. Implement secure shredding for documents. |  | Open
R-014 |  | Incident Response | No documented Incident Response Plan | External | 4 | 4 |  |  | Manager | Customize and distribute GSG-03 IRP. Conduct tabletop exercise within 30 days. |  | Open
R-015 |  | Incident Response | No cyber liability insurance | External | 3 | 5 |  |  | Owner | Obtain quotes from at least two cyber insurance providers. |  | Open
R-016 |  | Vendor Risk | No inventory of vendors with data access | External | 3 | 4 |  |  | Manager | Build vendor inventory. Review existing third-party access quarterly. |  | Open
R-017 |  | Vendor Risk | Vendor contracts lack breach notification clause | External | 2 | 4 |  |  | Owner / Legal | Add security addendum to vendor contracts at next renewal. |  | Open
R-018 |  | Security Awareness | No security awareness training program | Internal | 4 | 4 |  |  | Manager | Implement annual training. Enroll in KnowBe4 or CISA awareness resources. |  | Open
R-019 |  | Security Awareness | No phishing simulation conducted | Internal | 3 | 4 |  |  | IT Manager | Run phishing simulation using free tool. Identify high-risk staff for targeted training. |  | Open
R-020 |  | Cloud and Remote Work | No MFA on cloud platforms (MS365/GWS) | External | 5 | 5 |  |  | IT Manager | Enable MFA enforcement at tenant level. Enroll all admin accounts immediately. |  | Open

## Scoring Guide
RISK REGISTER — SCORING GUIDE
GSG-05 · Green Security Group · greensecuritygroup.com
LIKELIHOOD (F)
Score | Likelihood Rating | Description
1 | Rare | Unlikely to occur within 12 months given current controls
2 | Unlikely | May occur once every 1-3 years
3 | Possible | May occur once within the next 12 months
4 | Likely | Expected to occur multiple times within 12 months
5 | Almost Certain | Has occurred recently or expected imminently
IMPACT (G)
Score | Impact Rating | Description
1 | Negligible | Minimal disruption; easily resolved with no lasting effect
2 | Minor | Limited disruption; manageable with existing resources
3 | Moderate | Significant disruption; requires focused effort to resolve
4 | Major | Serious harm to operations, finances, or reputation; difficult to recover from
5 | Catastrophic | Existential threat to the business; potential regulatory, legal, or financial ruin
RISK LEVEL (H = F x G)
Score Range | Risk Level | Recommended Response
20-25 | CRITICAL | Immediate action required. Escalate to leadership. Implement compensating controls within 7 days.
12-19 | HIGH | Address within 30 days. Assign named owner. Track actively until resolved.
6-11 | MEDIUM | Address within 60-90 days. Include in next security review cycle.
1-5 | LOW | Monitor and review quarterly. Accept with documented rationale if mitigation cost exceeds risk.